## Slide 2: Scrum Under a Waterfall
Benjamin Day
DEV-B202

## Slide 3: Who’s heard of Scrum.org?

## Slide 4: Benjamin Day
Brookline, MA
Consultant, Coach, & Trainer
Microsoft MVP for Visual Studio ALM
Team Foundation Server, Software Testing, Scrum, Software Architecture
Scrum.org Classes
  Professional Scrum Developer (PSD)
  Professional Scrum Foundations (PSF)
www.benday.com, benday@benday.com, @benday

## Slide 5: Have you heard of Scrum.org?

## Slide 7: Online courses at Pluralsight

## Slide 8: Introductory Thoughts.

## Slide 9: What do I mean by “waterfall”?
Waterfall = plan-driven
Gaant charts
Microsoft Project
Start Dates & End Dates
Phases

## Slide 10: What is Scrum Under a Waterfall?
“Agile Under a Waterfall”
Scrum + plan-driven
Agile + plan-driven
SUW

## Slide 11: Assumptions
SUW exists
Value of Agile / Scrum is…
  Settled
  A good thing

## Slide 12: Agile is popular.
“Water-Scrum-Fall Is The Reality Of Agile For Most Organizations Today” by Dave West Forrester Research July 26, 2011

## Slide 13: Scrum is arguably the dominant Agile flavor.
“Water-Scrum-Fall Is The Reality Of Agile For Most Organizations Today” by Dave West Forrester Research July 26, 2011

## Slide 14: Agile seems to get results.
The CHAOS Manifesto, Copyright 2011

## Slide 15: My $0.02 on SUW
It’s a difficult place to be.
It’s a transitional form.
© Douglas Bray

## Slide 16: …and now a quote by a leading project management expert.

## Slide 17: “You can drive with your feet. It doesn’t mean it’s a good idea.” *
* - paraphrased

## Slide 18: So what do you do if your company does SUW?

## Slide 19: Two options.
Quit in protest. Get a new job.
Try to make it work.
  Someone else is paying.
  Make informed decisions.
  Lead the transition.

## Slide 20: Goal for this talk
Be practical
Try to see both sides
Acknowledge that change takes time

## Slide 21: Comparisons & Motivations.

## Slide 22: Waterfall vs. Scrum
Waterfall | Scrum / Agile
Requirements docs | Just-in-time, informal requirements
Occasional “customer” involvement | Frequent “customer” involvement
Start-to-finish Project Plan | Product Backlog. Plan for Sprint. Details are sketchy beyond that. Priorities shift based on new data.
Tasks are assigned | Assigned tasks are a bottleneck
Potentially large team size | Teams of 3 – 9 people
Multiple phases, eventual delivery | Working software each Sprint / Iteration
Resistant to change | Change is expected
Contract says what we build, deliver | Contract is a lot closer to T&E

## Slide 23: Why Waterfall?
Comes naturally
Feels good
  We’ve got a plan.
  We’ve got dates.
  What could possibly go wrong?
Helps managers manage
Pin down what’s going to be built
Minimize uncertainty
Notes: Waterfall
  comes naturally to people
  Feels good. We've got that plan with the date on it and, well, the team wrote that date down in that project plan so we're all set and my work it done here.
  It's a plan that's developed by the managers to coordinate what's going on.

## Slide 24: Why Scrum / Agile?
Embraces uncertainty
Empirical
“Forecast” rather than “commitment”
Self-organization and estimation by the “do-ers”
Notes: Agile
  Best summed up by someone throwing up their hands and saying "damned if I know"
  Throw in the ideas of emergent architecture and it looks like we have no idea and no plan.
  About self organizing teams and is by its nature driven by the "do-ers". The architects, developers, and testers.

## Slide 25: Who is Waterfall for?

## Slide 26: Ever seen a company that is Agile at the top and Waterfall at the bottom?

## Slide 27: Do managers trust their team? What does the team think about the managers?

## Slide 28: Why Waterfall people think Agile-ists are nuts
Sandal-wearing anarchists
Their estimates are always wrong
They’re always late
They’re lazy
The plan is flawless.
Devs write crummy, buggy code
“Too complex to not plan.”
Notes: Why Waterfall people think Agile people are FOS
  Our estimates are always wrong
  We're always late
  Those developers are totally lazy. If we didn't hit them with a cattle prod on a bi-daily basis, they'd look at facebook or ESPN.com until their eyes chapped over.
  My plan was awesome. It's the developers who are incompetent boobs. Look at this Gaant chart! It's a think of beauty.
  Why did the developers put so many bugs into the code? We should be almost done with the Testing phase by now and our bug count is astounding!
  We are the PMO. We know all. We see all.

## Slide 29: Why Agile-ists think Waterfall people are nuts
The plan is largely imposed
  “Voluntold”
What we told them was bogus.
  Haven’t the foggiest clue
  Just enough to make them go away
Didn’t have anything real to estimate anyway
“Too complex to plan.”
Notes: Why Agile people think Waterfall people are FOS
The plan is pretty much imposed on them with input from the team
    They're "voluntold" to be done by a date
  We told them what they wanted to hear to make them go away
  We haven't got the *foggiest* clue if we're right about the pieces, the amount of work, the order of work, the requirements, or the estimates. In fact, we're pretty sure -- no -- almost POSITIVE -- that the estimates are junk.
  We know that the requirements that we were "asked" to "estimate" are going to change a BILLION times before we get anywhere close to executing on them.

## Slide 30: Point of agreement #1: Each thinks the other side is wrong.

## Slide 31: Point of agreement #2: The work is complex.

## Slide 32: Making it work.

## Slide 33: SUW is the grumpy marriage of two processes.

## Slide 34: Why SUW?
Required by contract
Required by law
The Agile Experiment
Just cuz.

## Slide 35: Leverage the strengths of each
Scrum for day-to-day dev/test activities
Detect problems with Sprints
Focus on DoD & working software
Waterfall for multi-team coordination
Waterfall for release planning

## Slide 36: Differences for Scrum / Agile
Backlog = Project Plan
Less emphasis on Backlog Grooming & Sprint planning
Less negotiation during Sprint
Focus on ‘Definition of Done’
Daily Scrum
Sprint Burndown
Sprint Review
Retrospective
Same
Changed

## Slide 37: Some of the risks of SUW.

## Slide 38: Impedance mismatch leads to poor communication.

## Slide 40: Lack of trust & transparency.

## Slide 41: Culture of fear.

## Slide 42: A complete detachment from reality.

## Slide 43: Everything is going great until it isn’t.

## Slide 44: It’s two sets of books.

## Slide 45: Using metrics for evil.

## Slide 46: For example, Using the Burndown for Evil

## Slide 47: A lot of orgs are obsessed with individual performance.

## Slide 48: “Show it to me when it’s done.”

## Slide 49: So, uhhh…how do you make it work?

## Slide 50: Five tips.
Think positive.
Come to terms with uncertainty.
Fear is everywhere.
Avoid ‘earned value’.
Avoid keeping two sets of books.

## Slide 51: #1. Think positive.

## Slide 52: People get weird when their org starts thinking about getting more Agile.

## Slide 53: One problem is requiring people to think.

## Slide 54: Another major problem is the human fear of loss.

## Slide 55: Focus on what you gain rather than what you lose.

## Slide 56: Focus on ‘Done Software’.

## Slide 57: We’re going to get done software more often.

## Slide 58: You do have to get past change being a bug.

## Slide 59: It’s a chance to adapt. You get ‘done’ software and if you don’t like it, you can change it.

## Slide 60: It’s not “rework.”

## Slide 61: It’s improving existing features to better meet the needs of the stakeholders.

## Slide 62: Use the sprint boundaries as a way to take stock of where you are.

## Slide 63
“Strategy is the use of the engagement for the purpose of the war.”
from “On War” by Carl Phillip Gottfried von Clausewitz

## Slide 64: #2. Come to terms with uncertainty.

## Slide 65: Software is not a ‘sure thing.’

## Slide 66: Wishing does not make it so.

## Slide 67: Gripping tighter also does not make it so.

## Slide 68: Software always gets more complex once you start.

## Slide 69: Change is going to happen.

## Slide 70: Making your teams spend extra time on ‘more accurate planning’ is (probably) wasteful.

## Slide 71: Get to good enough and then stop.

## Slide 72: #3. Fear is everywhere.

## Slide 73: Managers, your developers are afraid of you.

## Slide 74: Executives, your managers are afraid of you and of your developers.

## Slide 75: Remember that your developers were picked on and bullied.

## Slide 76: If you make them nervous…

## Slide 77: …they know what you want to hear…

## Slide 78: …and they’ll tell it to you.

## Slide 79: (Unfortunately, it’s not true.)

## Slide 81: You need to try to create trust.

## Slide 82: You need to make it ok to be “wrong”.

## Slide 83: You need to make it ok for your teams to tell you that you are wrong.

## Slide 84: Too much consensus.

## Slide 85
“The goal of a leader should be to maximize resistance—in the sense of encouraging disagreement and dissent. … If you aren’t even aware that the people in the organization disagree with you, then you are in trouble.”
Leadership The Hard Way by Dov Frohman & Robert Howard

## Slide 86: #4. Avoid ‘earned value’.

## Slide 87: “I’m 72.6% done with my task.”

## Slide 88: …and now a quote by a leading project management expert.

## Slide 89
“[Earned value] is the path to the dark side. [Earned value] leads to [technical debt]. [Technical debt] leads to [maintainability problems]. [Maintainability problems] lead to suffering.”
Yoda, Star Wars: Episode 1

## Slide 90: Focus on your Definition of Done.

## Slide 91: It’s done or it isn’t. Done software only.

## Slide 92: (Oh…and force your team to write unit tests.)

## Slide 93: #5. Avoid keeping two sets of books.

## Slide 94: A shared reality is essential.

## Slide 95: Try to avoid the overhead of communicating between the two visions.

## Slide 96: Tip: Try Team Foundation Server + Microsoft Project Server

## Slide 97: Team Foundation Server & Visual Studio
One stop shop for your devs
Great tools for running an Agile / Scrum project.
Integrated with source control
Automated build system
QA testing tools for managing / tracking test suites and test progress
Feedback capture
Lightweight requirements

## Slide 98: Microsoft Project Server
Enterprise project management
  Tasks
  Portfolios of projects
  Timesheets
  Resources
  Approval workflows
Plug-in to SharePoint
Accessed via:
  Web interface
  Microsoft Project

## Slide 99: TFS & MPS Integration
Bi-directional sync
TFS data to/from Enterprise Project Plans

## Slide 100: TFS + Project Server Scenarios
Track progress across many teams for a large effort
  Think enterprise “roll-up”
Requirements in Project Server  Details created in TFS by the teams
  Project Server can approximate your “Product Backlog”
Modifications have an optional approval workflow
  Keeps Waterfall-centric managers in the loop

## Slide 101: Big win: Both groups stay in their preferred tools.

## Slide 102: Big win: Synchronization happens automatically.

## Slide 103: “Just the facts, ma’am.”
TFS captures data without judgment
Is it in source control?
Does the build work?
Do the tests pass?
What’s the bug count?
What’s the history on that work item?
Published to Project Server without judgment

## Slide 104: Demo: Requirements from MPS. Tasks from TFS.

## Slide 105: Demo: Approve changes & update dates.

## Slide 106: Demo: Manage Resource on an Enterprise Project Plan.

## Slide 107: Transparency & honesty is crucial for trust in SUW.

## Slide 108: Five tips.
Think positive.
Come to terms with uncertainty.
Fear is everywhere.
Avoid ‘earned value’.
Avoid keeping two sets of books.

## Slide 109: …in closing.

## Slide 110: Quick overview on Clausewitz.
http://www.bbc.co.uk/programmes/b01hl293
“In Our Time” BBC Radio 4 May 17, 2012

## Slide 111: The emotional overhead of discussing scope and other issues.
“Negotiating with Emotion” by Kimberlyn Leary, et al. Harvard Business Review January 2013

## Slide 112: Some thoughts on letting go.
“Yes To The Mess: Surprising Leadership Lessons from Jazz” by Frank J. Barrett Harvard Business Review Press

## Slide 113: On leadership style, communication, and failures.
“The Generals: American Military Command from World War II to Today” by Thomas E. Ricks

## Slide 114: Summary
SUW can be awkward
There can be trust problems
Use Scrum/Agile to detect problems
TFS & Project Server helps Project Management Impedance Mismatch
Transparency is the key

## Slide 115: Any last questions?

## Slide 116: Thank you.
http://www.benday.com | benday@benday.com